Career Path Generator

4-Day Project Roadmap & Team Execution Plan

Sunday, March 8 → Wednesday, March 12, 2026

5-Person Team | RAG-Powered | Groq LLaMA 3 | Next.js 15 | FastAPI

# 1. Project Overview

This document is the complete 4-day execution plan for the Career Path Generator — an AI-powered, RAG-based career roadmapping tool. The system takes a user profile (skills, experience, life stage) and generates an explainable, ethically-audited career transition roadmap using Groq LLaMA 3, ChromaDB, and a Python RAG microservice.

## Tech Stack Summary

| Layer | Technology | Owner |
| --- | --- | --- |
| Frontend | Next.js 15 + Tailwind CSS + TypeScript | Person 1 |
| Visualizations | React Flow + Recharts | Person 1 |
| Backend API | Node.js + Express + TypeScript + Zod | Person 2 |
| Auth & Cache | JWT + bcrypt + Redis (Upstash) | Person 2 |
| Database | Supabase PostgreSQL | Person 2 |
| RAG Pipeline | FastAPI + sentence-transformers + ChromaDB | Person 3 |
| LLM | Groq LLaMA 3 (free tier) | Person 3 |
| Web Scraping | Crawl4AI + Puppeteer/Cheerio | Person 4 |
| Knowledge Base | O*NET + BLS + Kaggle datasets → ChromaDB | Person 4 |
| Integration & DevOps | Vercel + Render + Docker + GitHub | Person 5 |

# 2. Team Roles & Responsibilities

| Person | Role | Primary Focus | Stack They Own |
| --- | --- | --- | --- |
| Person 1 | Frontend Engineer | All UI, pages, charts, roadmap visualizer | Next.js, Tailwind, React Flow, Recharts |
| Person 2 | Backend Engineer | API, auth, DB schema, Redis cache | Node.js, Express, Supabase, JWT, Redis |
| Person 3 | AI/RAG Engineer | RAG pipeline, LLM integration, embeddings | FastAPI, ChromaDB, sentence-transformers, Groq |
| Person 4 | Data Engineer | Web scraping, knowledge base, data pipeline | Crawl4AI, Cheerio, O*NET API, ChromaDB ingestion |
| Person 5 | Integration & DevOps | Connect all services, deploy, test end-to-end | Vercel, Render, Docker, GitHub Actions, Postman |

CRITICAL RULE: Every person exposes their work via clearly defined API contracts by end of Day 2 so Person 5 can integrate everything on Day 3.

# 3. API Contracts (Agree Before Day 1)

All team members must agree on these interfaces before writing any code. This prevents integration hell on Day 3.

## 3.1 Backend → Frontend Contracts (Person 2 exposes)

| Endpoint | Method | Input | Output |
| --- | --- | --- | --- |
| POST /api/auth/register | POST | { name, email, password } | { token, user } |
| POST /api/auth/login | POST | { email, password } | { token, user } |
| POST /api/profile | POST | { skills[], domain, experience, lifeStage } | { profileId, saved: true } |
| GET /api/profile/:id | GET | profileId in URL | { profile object } |
| POST /api/roadmap/generate | POST | { profileId } | { roadmap, auditScores, probability } |
| GET /api/roadmap/:id | GET | roadmapId in URL | { saved roadmap object } |
| GET /api/clusters | GET | — | { clusters[], demandScores[] } |

## 3.2 RAG Microservice Contracts (Person 3 exposes)

| Endpoint | Method | Input | Output |
| --- | --- | --- | --- |
| POST /rag/generate | POST | { profile: {...}, topK: 5 } | { roadmap, explanation, auditScores } |
| POST /rag/embed | POST | { text: string } | { embedding: float[] } |
| GET /rag/health | GET | — | { status: 'ok', chromadb: 'ok', groq: 'ok' } |

## 3.3 Data Pipeline Output (Person 4 produces)

| Collection | Format | Fields | Used By |
| --- | --- | --- | --- |
| career_docs | ChromaDB | id, text, metadata: {source, domain, type} | Person 3 RAG retrieval |
| job_market | JSON → ChromaDB | role, demand_score, growth, skills[] | Person 3 + Person 2 |
| career_clusters | PostgreSQL table | id, name, growth_trend, demand_score | Person 2 /api/clusters |

# 4. Day-by-Day Execution Plan

## DAY 1 — Sunday, March 8  |  Setup & Foundation

Goal: Every person has their environment running, base code scaffolded, and is ready to build features on Day 2. No feature work today — pure setup.

Person 1  — Frontend Engineer

📅 DAY 1  (Sunday)

- ⚙️ Scaffold Next.js 15 project  — npx create-next-app@latest career-path-gen --typescript --tailwind --app

- 📁 Create folder structure  — /app/(dashboard), /app/profile, /app/roadmap, /app/reports, /components/ui, /components/charts

- 🎨 Set up Tailwind config  — Add green palette: primary #004d40, secondary #00695c matching existing UI

- 📦 Install dependencies  — npm install react-flow-renderer recharts zustand @types/node

- 🖼️ Build static shell of all 4 pages  — Dashboard, Profile Input, Roadmap View, Reports — no real data yet, hardcoded placeholders

- 🔗 Set up Zustand store  — userStore (profile data), roadmapStore (generated output)

✅  All 4 pages render with placeholder UI — ready for real data hookup on Day 2

Person 2  — Backend Engineer

📅 DAY 1  (Sunday)

- ⚙️ Scaffold Node.js + TypeScript + Express project  — npx ts-node, install express, zod, bcrypt, jsonwebtoken, pg, prisma, ioredis

- 🗄️ Set up Supabase project  — Create tables: users, profiles, career_clusters, roadmaps, audit_results

- 📐 Write Prisma schema  — Define all models with correct relations and types

- 🔐 Implement auth routes  — POST /api/auth/register and POST /api/auth/login with JWT

- 📡 Set up Redis on Upstash  — Free tier — connect via ioredis, test ping

- ✅ Write Zod schemas  — ProfileSchema, RoadmapRequestSchema for all incoming requests

✅  Auth working (register/login returns JWT), DB connected, Redis connected

Person 3  — AI / RAG Engineer

📅 DAY 1  (Sunday)

- ⚙️ Set up Python environment  — python -m venv venv, pip install fastapi uvicorn chromadb sentence-transformers groq langchain

- 🤖 Set up Groq account  — Get free API key from console.groq.com, test LLaMA 3 call works

- 🗃️ Initialize ChromaDB  — Create local persistent ChromaDB instance, test add/query with dummy data

- 📡 Scaffold FastAPI app  — Create main.py with /rag/generate, /rag/embed, /rag/health endpoints — return dummy data for now

- 🧠 Test sentence-transformers  — Load all-MiniLM-L6-v2, encode a test sentence, confirm it works offline

- 📝 Write RAG prompt template  — System prompt: career advisor with PASSIONIT/PRUTL audit, injected context format

✅  FastAPI server runs, all 3 endpoints return dummy responses, Groq + ChromaDB both confirmed working

Person 4  — Data Engineer

📅 DAY 1  (Sunday)

- ⚙️ Set up Python scraping environment  — pip install crawl4ai cheerio requests pandas

- 📊 Download Kaggle career datasets  — Job skills dataset, career transition dataset — save as CSV

- 🌐 Test O*NET API  — Register at onetonline.org/developer, test /careers and /skills endpoints

- 🕷️ Write Crawl4AI scraper  — Target: Naukri.com job listings for top 10 domains — output clean JSON

- 🔄 Write data cleaning script  — Normalize all sources into unified format: { role, skills[], domain, demand, description }

✅  At least 200 clean career documents in unified JSON format ready to embed on Day 2

Person 5  — Integration & DevOps

📅 DAY 1  (Sunday)

- 📁 Create GitHub monorepo  — Folders: /frontend, /backend, /rag-service, /data-pipeline — invite all team members

- 🔧 Set up GitHub Actions  — Basic CI: lint + typecheck on every push to main

- 🌐 Deploy frontend to Vercel  — Connect GitHub repo, set env vars, confirm auto-deploy works

- 🖥️ Deploy backend to Render  — Create Node.js web service, set PORT and DB env vars

- 🐳 Write Dockerfile for RAG service  — Python 3.11 + all dependencies, expose port 8000

- 📋 Create shared .env.example  — Document every env variable needed across all 3 services — share with team

- 📬 Set up Postman collection  — Add all API endpoints from Section 3 as empty requests ready to test

✅  GitHub repo live, Vercel + Render both deploying, Postman collection shared with team

## DAY 2 — Monday, March 9  |  Core Feature Build

Goal: Every person builds their core feature completely. By end of day, individual pieces work in isolation. Do not wait for other people — use mock data where needed.

Person 1  — Frontend Engineer

📅 DAY 2  (Monday)

- 📋 Build Profile Input Form  — Multi-step form: Step 1 skills/domain, Step 2 experience/life stage — save to Zustand on submit

- 📊 Build Dashboard page  — Fetch /api/clusters, render Recharts bar chart (demand scores) + alignment overview stats

- 🗺️ Build Roadmap Visualizer  — React Flow nodes: each career milestone = node, transitions = edges, clicking node shows skill requirements

- 📈 Build Reports page  — PASSIONIT/PRUTL scores table, skill gap radar chart using Recharts

- 🔐 Add auth pages  — Login + Register forms, store JWT in Zustand, add protected route wrapper

- 🔄 Wire up API calls  — All fetch calls point to backend URL from env var — mock responses if backend not ready

✅  Complete frontend works with mock data — all pages functional, charts rendering, React Flow roadmap displays

⚠️  Use this mock roadmap JSON for React Flow testing: { nodes: [{id:'1', label:'Engineer'}, {id:'2', label:'Tech Lead'}], edges: [{source:'1', target:'2'}] }

Person 2  — Backend Engineer

📅 DAY 2  (Monday)

- 👤 Build profile endpoints  — POST /api/profile (save), GET /api/profile/:id (fetch) — validate with Zod, save to Supabase

- 🚀 Build roadmap generation endpoint  — POST /api/roadmap/generate — receives profileId, fetches profile, calls RAG microservice, caches result in Redis, saves to DB

- 💾 Build Redis caching layer  — Cache key = hash of profile data, TTL = 24 hours — check cache before calling RAG service every time

- 🏢 Seed career clusters  — Insert 20+ career clusters into Supabase with demand scores, GET /api/clusters returns them

- 🔗 Wire backend → RAG service  — HTTP call to FastAPI /rag/generate with profile data — handle errors and timeouts (set 30s timeout)

✅  All API endpoints working, tested in Postman, Redis caching confirmed (second identical request returns cached response)

Person 3  — AI / RAG Engineer

📅 DAY 2  (Monday)

- 📥 Build embedding pipeline  — Accept Person 4's JSON → sentence-transformers embed each doc → store in ChromaDB with metadata

- 🔍 Build retrieval logic  — Given user profile text, embed it → query ChromaDB top-5 → return relevant career docs

- 🧠 Build LLM prompt chain  — Inject retrieved docs + user profile into system prompt → call Groq LLaMA 3 → parse output

- 📊 Build ethical audit output  — Second Groq call with PASSIONIT/PRUTL prompt → return scores as JSON { dimension, score, risk, explanation }

- ⚡ Implement /rag/generate fully  — End-to-end: profile in → retrieve → generate roadmap → audit → return structured JSON

- 🛡️ Add error handling  — Groq rate limit retry logic (exponential backoff), ChromaDB connection error fallback

✅  Full RAG pipeline working end-to-end — test with 3 different profiles, all return valid roadmaps + audit scores

Person 4  — Data Engineer

📅 DAY 2  (Monday)

- 📤 Run embedding pipeline  — Hand off cleaned JSON to Person 3's embedding script — embed all 200+ docs into ChromaDB

- 🌐 Scrape live job data  — Run Crawl4AI on Naukri/LinkedIn Jobs for top domains — add 100+ real job listings to knowledge base

- 📡 Pull O*NET data  — Fetch career descriptions, skills, tasks for 30+ occupations — chunk and embed into ChromaDB

- 🗃️ Load career_clusters into Supabase  — Format cluster data as SQL seed file, share with Person 2 to insert into DB

- 🔁 Build update script  — Script that re-scrapes + re-embeds weekly — document how to run it

✅  ChromaDB has 300+ embedded career documents across all major domains — Person 3 can query it and get relevant results

Person 5  — Integration & DevOps

📅 DAY 2  (Monday)

- 🧪 Test all Day 1 endpoints  — Run through entire Postman collection — document which work, which return errors

- 🐳 Deploy RAG service to Hugging Face Spaces  — Push Docker image, set GROQ_API_KEY env var, confirm /rag/health returns ok

- 🔧 Set all environment variables  — Vercel: NEXT_PUBLIC_API_URL. Render: DATABASE_URL, REDIS_URL, RAG_SERVICE_URL. HF: GROQ_API_KEY

- 🔗 Test cross-service communication  — Backend on Render calling RAG service on HF Spaces — confirm HTTP calls work in production

- 📋 Write integration test script  — Bash script that hits every endpoint in sequence: register → login → create profile → generate roadmap

✅  All 3 services deployed and talking to each other in production — integration test script passes

## DAY 3 — Tuesday, March 10  |  Integration & Connection

Goal: Connect everything together. Frontend talks to backend. Backend talks to RAG service. Real data flows through the entire system. Person 5 leads this day.

Person 1  — Frontend Engineer

📅 DAY 3  (Tuesday)

- 🔌 Replace ALL mock data with real API calls  — Profile form → POST /api/profile. Dashboard → GET /api/clusters. Roadmap → POST /api/roadmap/generate

- ⏳ Add loading states  — Spinner while roadmap generates (LLM takes 5-15s), skeleton loaders for dashboard charts

- ❌ Add error handling UI  — Toast notifications for API errors, retry button if roadmap generation fails

- 🗺️ Map real roadmap JSON to React Flow  — Parse roadmap text from LLM → convert to nodes/edges structure React Flow expects

- 📊 Map real audit scores to Reports page  — Parse PASSIONIT/PRUTL JSON → render in table + radar chart

- 📱 Make UI responsive  — Mobile breakpoints for all pages — Tailwind sm: md: lg: classes

✅  Complete user journey works: Register → Fill Profile → Generate Roadmap → View on React Flow → See Audit Report

Person 2  — Backend Engineer

📅 DAY 3  (Tuesday)

- 🐛 Fix any API bugs found by Person 5  — Respond quickly to integration issues — this is the most critical day for backend

- 📊 Add roadmap history endpoint  — GET /api/roadmap/history/:userId — returns all past roadmaps for a user

- 🔒 Add auth middleware  — Protect all non-auth endpoints with JWT verification middleware

- ⚡ Optimize DB queries  — Add indexes on users.email, profiles.userId, roadmaps.userId

- 📝 Add request logging  — Log all requests with timestamp, endpoint, response time — helps debug integration issues

✅  All endpoints secured, history working, no integration blockers for Person 5

Person 3  — AI / RAG Engineer

📅 DAY 3  (Tuesday)

- 🐛 Fix any RAG output format issues  — Person 5 will report if LLM output isn't parsing correctly — fix JSON structure

- 🎯 Improve prompt quality  — Test with 5 different profile types — refine system prompt for better roadmap quality

- ⚡ Optimize retrieval  — Tune ChromaDB topK and similarity threshold — ensure retrieved docs are actually relevant

- 🔄 Add streaming support (optional)  — Stream LLM tokens back to frontend for better UX — skip if time-constrained

- 📊 Validate audit scores  — Ensure PASSIONIT/PRUTL scores are consistent and not hallucinated — add output validation

✅  RAG pipeline stable, outputs consistent JSON every time, no parsing failures

Person 4  — Data Engineer

📅 DAY 3  (Tuesday)

- 📈 Expand knowledge base  — Add more domain-specific docs — focus on gaps Person 3 reports during testing

- 🔍 Quality check embeddings  — Query ChromaDB with test profiles — verify retrieved docs are relevant to the profile domain

- 🌐 Scrape salary & demand data  — Add compensation data to knowledge base — makes roadmaps more realistic

- 📋 Document data pipeline  — Write README: how to re-run scraper, how to re-embed, how to add new data sources

✅  Knowledge base complete and high quality — at least 500 documents, all domains covered

Person 5  — Integration & DevOps

📅 DAY 3  (Tuesday)

- 🔗 Run full integration test  — Complete user journey from registration to roadmap generation in production environment

- 🐛 Triage and assign all bugs  — Document every issue found, assign to correct person, set priority (blocker vs nice-to-have)

- 📊 Performance testing  — Measure end-to-end latency: profile submit → roadmap displayed. Target: under 20 seconds

- 🔧 Fix CORS issues  — Ensure all cross-origin requests work between Vercel frontend and Render backend

- 🔐 Security check  — Verify JWT required on protected routes, no API keys exposed in frontend code

- 📹 Record demo video  — Screen record the working flow — useful for Day 4 presentation

✅  Full system works end-to-end in production, all blockers resolved, demo recorded

## DAY 4 — Wednesday, March 11  |  Polish & Finalize

Goal: Fix remaining bugs, polish UI, write documentation, prepare demo. No new features after 12pm — only fixes and polish.

Person 1  — Frontend Engineer

📅 DAY 4  (Wednesday — Morning Only for Features)

- ✨ UI polish  — Consistent spacing, typography, color — match the green #004d40 theme throughout

- 🎨 Improve React Flow roadmap  — Custom node styles, animated edges, zoom controls, mini-map

- 📊 Animate charts  — Recharts entry animations for dashboard — makes it look professional

- 🔔 Add success states  — Celebration animation when roadmap generates, clear empty states when no data

- 🐛 Fix all reported UI bugs  — Address everything from Person 5's Day 3 bug list

✅  UI is polished, professional, and consistent — no visual bugs

Person 2  — Backend Engineer

📅 DAY 4  (Wednesday)

- 🐛 Fix any remaining backend bugs  — Priority: anything blocking the demo flow

- 📊 Add analytics endpoint  — GET /api/analytics/summary — powers dashboard stats (total profiles, alignment distribution)

- 📝 Write API documentation  — Document all endpoints with request/response examples — use Postman or simple README

- 🔧 Environment hardening  — Ensure all secrets in env vars, no hardcoded values, production DB separate from dev

✅  Backend stable, documented, no crashes under normal demo load

Person 3  — AI / RAG Engineer

📅 DAY 4  (Wednesday)

- 🧪 Final prompt tuning  — Run 10 test profiles — ensure outputs are high quality, specific, and not generic

- 📊 Validate ethical audit  — All PASSIONIT/PRUTL dimensions must return scores — fix any missing dimensions

- 📝 Document RAG architecture  — Diagram + explanation of how retrieval works — for presentation

- 💡 Add fallback responses  — If Groq is rate limited, return cached similar profile response from Redis

✅  RAG outputs high quality, consistent, ethical audit complete for all test profiles

Person 4  — Data Engineer

📅 DAY 4  (Wednesday)

- ✅ Final knowledge base audit  — Check all domains represented, no duplicate documents, metadata correct

- 📋 Write data documentation  — Sources used, document count per domain, how to update

- 🎯 Create demo-specific data  — Ensure the exact demo scenario (Engineer → Burnout → Teaching) has rich documents in ChromaDB

- 🔁 Test update pipeline  — Run full scrape → clean → embed cycle once more to confirm it works end-to-end

✅  Knowledge base is demo-ready, documented, and reproducible

Person 5  — Integration & DevOps

📅 DAY 4  (Wednesday)

- 🎬 Prepare demo script  — Write exact click-by-click demo flow using the Engineer → Burnout → Teaching scenario

- 🔧 Final deployment check  — All 3 services latest code deployed, env vars correct, health checks green

- 📁 Clean up GitHub  — Remove debug logs, merge all branches to main, tag release v1.0

- 📊 Create project summary doc  — Tech stack, architecture diagram, what was built, what can be extended

- 🧪 Final end-to-end test  — Run demo script 3 times — confirm it works consistently

✅  Demo ready, all services stable, GitHub clean, project documented

# 5. Daily Sync Structure

Every day at 9:00 AM and 9:00 PM — 15 minutes maximum. Use a WhatsApp group or Discord.

| Time | What to Share | Duration |
| --- | --- | --- |
| 9:00 AM Standup | What I'm building today + any blockers from yesterday | 15 min |
| 9:00 PM Check-in | What I delivered + anything blocking tomorrow's work | 15 min |
| Ad-hoc | If you're blocked for more than 1 hour — message the group immediately | As needed |

## Blocker Protocol

- If blocked for less than 1 hour — try to solve it yourself

- If blocked for more than 1 hour — message the group immediately, don't wait for standup

- Person 5 is the integration coordinator — they have final say on API contract disputes

- If Groq rate limits hit — Person 3 switches to cached responses while waiting for reset

# 6. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Groq rate limits during demo | Medium | High | Redis cache identical queries, have 2-3 pre-generated roadmaps ready as fallback |
| ChromaDB returns irrelevant docs | Medium | High | Person 4 must add domain-tagged metadata, Person 3 filters by metadata before ranking |
| LLM output format unpredictable | High | High | Always ask Groq to respond in strict JSON, add output validation + retry if parse fails |
| Render free tier cold start (30s) | High | Medium | Use UptimeRobot to ping backend every 5 min keeping it warm |
| HF Spaces slow Docker boot | Medium | Medium | Keep RAG service always warm, or pre-generate for demo profiles |
| CORS errors in production | Medium | Medium | Set CORS headers on Day 1 — don't leave for Day 3 |
| Team member falls behind | Low | High | Person 5 identifies on Day 2 PM check-in, team redistributes tasks immediately |

# 7. Final Deliverables Checklist

| # | Deliverable | Owner | Done? |
| --- | --- | --- | --- |
| 1 | Next.js frontend deployed on Vercel | Person 1 | ☐ |
| 2 | React Flow career roadmap visualizer working | Person 1 | ☐ |
| 3 | Recharts dashboard (demand scores, alignment) | Person 1 | ☐ |
| 4 | All API endpoints working + JWT auth | Person 2 | ☐ |
| 5 | Redis caching on roadmap generation | Person 2 | ☐ |
| 6 | Supabase DB seeded with clusters + schema | Person 2 | ☐ |
| 7 | RAG pipeline end-to-end working | Person 3 | ☐ |
| 8 | PASSIONIT/PRUTL ethical audit output | Person 3 | ☐ |
| 9 | Groq LLaMA 3 generating quality roadmaps | Person 3 | ☐ |
| 10 | ChromaDB with 500+ embedded career docs | Person 4 | ☐ |
| 11 | Web scraping pipeline documented + rerunnable | Person 4 | ☐ |
| 12 | All 3 services deployed + talking to each other | Person 5 | ☐ |
| 13 | Demo script works 3 times in a row | Person 5 | ☐ |
| 14 | GitHub repo clean, README complete | Person 5 | ☐ |

Build fast. Ship it. Good luck. 🚀